PMBOK Chapter 4 (Project Integration Management)

Study Notes Submitted by Jesse Steele

Project Integration Management includes the processes required to ensure that the

various elements of the project are properly coordinated. It involves making tradeoffs

among competing objectives and alternatives in order to meet or exceed stake-holder

needs and expectations. While all project management processes are integrative

to some extent, the processes described in this chapter are primarily

integrative. Figure 4–1 provides an overview of the following major processes:

4.1 Project Plan Development—taking the results of other planning processes

and putting them into a consistent, coherent document.

4.2 Project Plan Execution—carrying out the project plan by performing the

activities included therein.

4.3 Overall Change Control—coordinating changes across the entire project.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more individuals

or groups of individuals based on the needs of the project. Each process generally

occurs at least once in every project phase.

4.1 PROJECT PLAN DEVELOPMENT

Project plan development uses the outputs of the other planning processes to create

a consistent, coherent document that can be used to guide both project execution

and project control. The project plan is used to:

• Guide project execution.

• Document project planning assumptions.

• Document project planning decisions regarding alternatives chosen.

• Facilitate communication among stakeholders.

• Define key management reviews as to content, extent, and timing.

• Provide a baseline for progress measurement and project control.

4.1.1 Inputs to Project Plan Development

.1 Other planning outputs. Other planning outputs include both base documents such as the work breakdown structure as well as the supporting detail. Many projects will also require application area-specific inputs (e.g., most construction projects will require a cash flow forecast).

.2 Historical information. The available historical information (e.g., estimating databases,

records of past project performance) should have been consulted during the

other project planning processes. This information should also be available during

project plan development to assist with verifying assumptions and assessing alternatives

that are identified as part of this process.

.3 Organizational policies. Organi-zational policies which typically must be considered include, but are not limited to:

• Quality management—process audits, continuous improvement targets.

• Personnel administration—hiring and firing guidelines, employee performance

reviews.

• Financial controls—time reporting, required expenditure and disbursement

reviews, accounting codes, standard contract provisions.

.4 Constraints. Constraints are factors that will limit the project management team’s

options. For example, a predefined budget is a constraint that is highly likely to limit

the team’s options regarding scope, staffing, and schedule.

.5 Assumptions. Assumptions are factors that, for planning purposes, will be considered

to be true, real, or certain. For example, if the date that a key person will become

available is uncertain, the team may assume a specific start date.

Inputs Tools & Techniques Outputs

- Tools and Techniques for Project Plan Development

.1 Project planning methodology. A project planning methodology is any structured

approach used to guide the project team during development of the project plan. It

may be as simple as standard forms and templates (whether paper or electronic, formal

or informal) or as complex as a series of required simulations (e.g., Monte Car-lo

analysis of schedule risk).

.2 Stakeholder skills and knowledge. Every stakeholder has skills and knowledge

which may be useful in developing the project plan. The project management team

must create an environment in which the stakeholders can contribute appropriately. Who contributes, what they con-tribute, and when will vary. For example:

• On a construction project being done under a lump sum contract, the professional

cost engineer will make a major contribution to the profitability objective

during proposal preparation when the contract amount is being determined.

• On a project where staffing is defined in advance, the individual contributors

may contribute significantly to meeting cost and schedule objectives by re-viewing

duration and effort estimates for reasonableness.

.3 Project management information system (PMIS). A project management information

system consists of the tools and techniques used to gather, integrate, and disseminate

the outputs of the other project management processes. It is used to sup-port

all aspects of the project from initiating through closing and generally includes

both manual and automated systems.

- Outputs from Project Plan Development

.1 Project plan. The project plan is a formal, approved document used to manage and

control project execution. It should be distributed as defined in the communications

management plan (e.g., management of the performing organization may re-quire

broad coverage with little detail, while a contractor may require complete de-tails

on a single subject).    There are many ways to organize and present the project plan, but it commonly in-cludes all of the following (these items are described in more detail elsewhere):

• Project charter.

• A description of the project management approach or strategy (a summary of

the individual management plans from the other knowledge areas).

• Scope statement, which includes the project deliverables and the project objectives.

• Work breakdown structure (WBS) to the level at which control will be exercised.

• Cost estimates, scheduled start dates, and responsibility assignments to the level

of the WBS at which control will be exercised.

• Performance measurement baselines for schedule and cost.

• Major milestones and target dates for each.

• Key or required staff.

• Key risks, including constraints and assumptions, and planned responses for each.

• Subsidiary management plans, including scope management plan, schedule

management plan, etc.

• Open issues and pending decisions.

.2 Supporting detail. Supporting detail for the project plan includes:

• Outputs from other planning processes that are not included in the project plan.

• Additional information or documentation generated during development of

the project plan (e.g., constraints and assumptions that were not previously

known).

• Technical documentation such as requirements, specifications, and designs.

• Documentation of relevant standards.

This material should be organized as needed to facilitate its use during project

plan execution.

4.2 PROJECT PLAN EXECUTION

Project plan execution is the primary process for carrying out the project plan—the

vast majority of the project’s budget will be expended in performing this process.

- Inputs to Project Plan Execution

.1 Project plan. The subsidiary management plans (scope management plan, risk management plan, procurement management plan, etc.) and the performance measurement baselines are key inputs to project plan execution.

.2 Supporting detail. Supporting detail is described in Section 4.1.3.2.

.3 Organizational policies.    Any and all of the organizations involved in the project may have formal and informal policies which may affect project plan execution.

.4 Corrective action. Corrective action is anything done to bring expected future project

performance into line with the project plan. Corrective action is an output of

the various control processes—as an input here it completes the feedback loop

needed to ensure effective project management.

- Tools and Techniques for Project Plan Execution

.1 General management skills. General management skills such as leadership, communicating,

and negotiating are essential to effective project plan execution.

.2 Product skills and knowledge. The project team must have access to an appropriate

set of skills and knowledge about the project product. The necessary skills are defined

as part of planning (especially in resource planning, Section 7.1) and are provided

through the staff acquisition process (described in Section 9.2).

.3 Work authorization system. A work authorization system is a formal procedure for

sanctioning project work to ensure that work is done at the right time and in the

proper sequence.

.4 Status review meetings. Status review meetings are regularly scheduled meetings

held to exchange information about the project.

.5 Project management information system. The project management information

system is described in Section 4.1.2.3.

.6 Organizational procedures. Any and all of the organizations involved in the project

may have formal and informal procedures useful during project execution.

- Outputs from Project Plan Execution

.1 Work results. Work results are the outcomes of the activities performed to accomplish

the project. Information on work results—which deliverables have been completed and which have not, to what extent quality standards are being met, what costs have been incurred or committed, etc.—is collected as part of project plan execution and fed into the performance reporting process

.2 Change requests. Change requests (e.g., to expand or contract project scope, to modify cost or schedule estimates, etc.) are often identified while the work of the project is being done.

- OVERALL CHANGE CONTROL

Overall change control is concerned with (a) influencing the factors which create changes to ensure that changes are beneficial, (b) determining that a change has occurred, and (c) managing the actual changes when and as they occur.

Overall change control requires:

• Maintaining the integrity of the performance measurement baselines—all approved

changes should be reflected in the project plan, but only project scope

changes will affect the performance measurement baselines.

• Ensuring that changes to the product scope are reflected in the definition of

the project scope (the difference between product and project scope is discussed

in the introduction to Chapter 5).

• Coordinating changes across knowledge areas as illustrated in Figure 4–2. For

example, a proposed schedule change will often affect cost, risk, quality, and

staffing.

- Inputs to Overall Change Control

.1 Project plan. The project plan provides the baseline against which changes will be

controlled (see Section 4.1.3.1).

.2 Performance reports. Performance reports (described in Section 10.3) provide information

on project performance. Performance reports may also alert the project team to issues which may cause problems in the future.

.3 Change requests. Change requests may occur in many forms—oral or written, direct or indirect, externally or internally initiated, and legally mandated or optional.

- Tools and Techniques for Overall Change Control

.1 Change control system. A change control system is a collection of formal, documented

procedures that defines the steps by which official project documents may

be changed. It includes the paperwork, tracking systems, and approval levels necessary

for authorizing changes.

.2 Configuration management. Configuration management is any documented procedure

used to apply technical and administrative direction and surveillance to:

• Identify and document the functional and physical characteristics of an item or

system.

• Control any changes to such characteristics.

• Record and report the change and its implementation status.

• Audit the items and system to verify conformance to requirements [1].

In many application areas, configuration management is a subset of the change

control system and is used to ensure that the description of the project product is

correct and complete. However, in some application areas, the term configuration

management is used to describe any rigorous change control system.

.3 Performance measurement. Performance measurement techniques such as earned

value (described in Section 10.3.2.4) help to assess whether variances from the plan

require corrective action.

.4 Additional planning. Projects seldom run exactly according to plan. Prospective

changes may require new or revised cost estimates, modified activity sequences, analy-sis

of risk response alternatives, or other adjustments to the project plan.

.5 Project management information system. Project management information systems

are described in Section 4.1.2.3.

- Outputs from Overall Change Control

.1 Project plan updates. Project plan updates are any modification to the contents of

the project plan or the supporting detail (described in Sections 4.1.3.1 and 4.1.3.2,

respectively). Appropriate stakeholders must be notified as needed.

.2 Corrective action. Corrective action is described in Section 4.2.1.4.

.3 Lessons learned. The causes of variances, the reasoning behind the corrective action

chosen, and other types of lessons learned should be documented so that they become

part of the historical database for both this project and other projects of the

performing organization.